## Sheet1
OVERVIEW OF THE UNITED STATES SOFTWARE INDUSTRY RESULTS CIRCA 2008
2008-04-16
Copyright © 2008 by Capers Jones & Associates LLC. All rights reserved.
Capers Jones | email: CJonesiii@cs.com
Note 1: Data for software projects of 1,000,000 function point size is hypothetical, since no projects of that size exist circa 2008.
Note 2: Data assumes IFPUG function points, version 4.2.
Note 3: The spreadsheets omit the entertainment and games industries due to lack of data.
Note 4: The data is preliminary and has a high margin of error. It is provided for calibration and correction purposes only.
Note 5: Average values are misleading, since the ranges in both directions can vary by more than 2 to 1.
Note 6: Sample size is only about 13,000 projects, which is too small for accuracy.
Note 7: Projects > 10,000 function points are extremely hazardous
Note 8: Quality control of U.S. software is not adequate circa 2008.
Note 9: Security control of U.S. software is not adequate circa 2008.
Note 10: U.S. software is aging faster than it is replaced, and decaying faster than it is renovated.
Table 1: Average Schedules in Calendar Months by Type and Size of Software Project
(Note: Schedules run from start of requirments until delivery to initial customers.)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
10 | 0.35 | 0.25 | 0.33 | 0.6 | 0.7 | 0.9 | 1 | 0.59
100 | 4 | 3 | 3.5 | 4.5 | 4 | 5.5 | 7 | 4.5
1000 | 12 | 10 | 11 | 14 | 13 | 15 | 18 | 13.2857
10000 | 44 | 37 | 42 | 41 | 42 | 46 | 48 | 42.8571
100000 | 62 | 56 | 58 | 57 | 58 | 63 | 66 | 60
1000000 | 74 | 68 | 70 | 68 | 69 | 78 | 80 | 72.4286
Average | 28.0514 | 24.8943 | 26.4057 | 26.4443 | 26.6729 | 29.7729 | 31.43 | 27.6673
Table 2: Average Staff Headcount by Type and Size of Software Project
(Note: All technical personnel and project managers are assumed.)
|  |  |  | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
100 | 1.3333 | 1.5385 | 1.3333 | 1.4286 | 1.4085 | 1.6667 | 1.7544 | 1.4947
1000 | 5.8824 | 5.7471 | 6.0606 | 6.0976 | 6.3291 | 6.4516 | 7.0423 | 6.2301
10000 | 61.7284 | 59.5238 | 60.9756 | 62.5 | 64.1026 | 64.5161 | 66.6667 | 62.859
100000 | 632.9114 | 625 | 617.284 | 641.0256 | 628.9308 | 649.3506 | 675.6757 | 638.5969
1000000 | 6410.2564 | 6134.9693 | 6329.1139 | 6451.6129 | 6535.9477 | 6578.9474 | 6756.7568 | 6456.8006
Average | 1016.3017 | 975.5398 | 1002.3953 | 1023.5235 | 1034.1027 | 1043.2761 | 1072.8422 | 1023.9973
Table 3: Average Effort in Person Months by Type and Size of Software Project
(Note: All technical personnel and project managers are assumed.)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
10 | 0.35 | 0.25 | 0.33 | 0.6 | 0.7 | 0.9 | 1 | 0.59
100 | 5.3333 | 4.6154 | 4.6667 | 6.4286 | 5.6338 | 9.1667 | 12.2807 | 6.875
1000 | 70.5882 | 57.4713 | 66.6667 | 85.3659 | 82.2785 | 96.7742 | 126.7606 | 83.7008
10000 | 2716.0494 | 2202.381 | 2560.9756 | 2562.5 | 2692.3077 | 2967.7419 | 3200 | 2700.2794
100000 | 39240.5063 | 35000 | 35802.4691 | 36538.4615 | 36477.9874 | 40909.0909 | 44594.5946 | 38366.1586
1000000 | 474358.9744 | 417177.9141 | 443037.9747 | 438709.6774 | 450980.3922 | 513157.8947 | 540540.5405 | 468280.4811
Average | 73770.2588 | 64920.3774 | 68781.8704 | 68271.8633 | 70034.1871 | 79591.6541 | 84067.8838 | 72776.8707
Table 4: Average Productivity Rates in Function Points per Staff Month by Type and Size of Software Project
(Note: Complete life cycle from start of requirements to delivery is assumed. Technical workers and managers are assumed.)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
10 | 28.5714 | 40 | 30.303 | 16.6667 | 14.2857 | 11.1111 | 10 | 21.5626
100 | 18.75 | 21.6667 | 21.4286 | 15.5556 | 17.75 | 10.9091 | 8.1429 | 16.3147
1000 | 14.1667 | 17.4 | 15 | 11.7143 | 12.1538 | 10.3333 | 7.8889 | 12.6653
10000 | 3.6818 | 4.5405 | 3.9048 | 3.9024 | 3.7143 | 3.3696 | 3.125 | 3.7483
100000 | 2.5484 | 2.8571 | 2.7931 | 2.7368 | 2.7414 | 2.4444 | 2.2424 | 2.6234
1000000 | 2.1081 | 1.1371 | 0.94163 | 1.0099 | 0.97279 | 0.87883 | 0.83431 | 1.1261
Average | 24.2609 | 26.8002 | 24.9102 | 21.6551 | 21.6597 | 19.8638 | 18.8905 | 22.5772
Table 5: Average Burdened Cost by Type and Size of Software Projects
(Note: Burden or overhead rates and average compensation vary by more than 50% in either direction)
|  |  |  | Systems & |  | Civilian
| MIS | Web | Domestic | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Compensation | 6500 | 9200 | 5750 | 9000 | 6300 | 6200 | 6100 | 7007.1429
Burden % | 50% | 55% | 70% | 50% | 60% | 75% | 125% | 69.29%
Burdened cost | 9750 | 14260 | 9775 | 13500 | 10080 | 10850 | 13725 | 11705.7143
Size in FP
1 | 97.5 | 142.6 | 97.75 | 135 | 100.8 | 108.5 | 137.25 | 117.0571
10 | 3412.5 | 3565 | 3225.75 | 8100 | 7056 | 9765 | 13725 | 6978.4643
100 | 52000 | 65815.3846 | 45616.6667 | 86785.7143 | 56788.7324 | 99458.3333 | 168552.6316 | 82145.3518
1000 | 688235.2941 | 819540.2299 | 651666.6667 | 1152439.0244 | 829367.0886 | 1050000 | 1739788.7324 | 990148.148
10000 | 26481481.4815 | 31405952.381 | 25033536.5854 | 34593750 | 27138461.5385 | 32200000 | 43920000 | 31539025.998
100000 | 382594936.7089 | 499100000 | 349969135.8025 | 493269230.7692 | 367698113.2075 | 443863636.3636 | 612060810.8108 | 449793694.8089
1000000 | 4625000000 | 5948957055.2147 | 4330696202.5316 | 5922580645.1613 | 4545882352.9412 | 5567763157.8947 | 7418918918.9189 | 5479971190.3804
Average | 719260023.3549 | 925764581.5443 | 672342783.1075 | 921670155.0956 | 705944605.7583 | 863569446.5845 | 1153831704.7634 | 851769042.8869
Table 6: Average Cost per Function Point by Type and Size of Software Projects
(Note: Burden or overhead rates and average compensation vary by more than 50% in either direction)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Compensation | 6500 | 9200 | 5750 | 9000 | 6300 | 6200 | 6100 | 7007.1429
Burden rate | 50% | 55% | 70% | 50% | 60% | 75% | 125% | 69.29%
Burdened cost | 9750 | 14260 | 9775 | 13500 | 10080 | 10850 | 13725 | 11705.7143
Size in FP
1 | 97.5 | 142.6 | 97.75 | 135 | 100.8 | 108.5 | 137.25 | 117.0571
10 | 341.25 | 356.5 | 322.575 | 810 | 705.6 | 976.5 | 1372.5 | 697.8464
100 | 520 | 658.1538 | 456.1667 | 867.8571 | 567.8873 | 994.5833 | 1685.5263 | 821.4535
1000 | 688.2353 | 819.5402 | 651.6667 | 1152.439 | 829.3671 | 1050 | 1739.7887 | 990.1481
10000 | 2648.1481 | 3140.5952 | 2503.3537 | 3459.375 | 2713.8462 | 3220 | 4392 | 3153.9026
100000 | 3825.9494 | 4991 | 3499.6914 | 4932.6923 | 3676.9811 | 4438.6364 | 6120.6081 | 4497.9369
1000000 | 4625 | 5948.9571 | 4330.6962 | 5922.5806 | 4545.8824 | 5567.7632 | 7418.9189 | 5479.9712
Average | 1820.869 | 2293.9066 | 1694.5571 | 2468.5634 | 1877.1949 | 2336.569 | 3266.656 | 2251.188
Table 7: Average Defect Potential per Function Point by Type and Size of Software Projects
(Note: Defect potential includes requirements, design, code, document, and bad-fix defect categories)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
10 | 2.25 | 2 | 2 | 2.5 | 2 | 2.7 | 2.9 | 2.3357
100 | 2.8 | 2.5 | 2.5 | 3 | 3.15 | 3.3 | 4 | 3.0357
1000 | 4.3 | 4.25 | 4 | 4.3 | 4.75 | 5.25 | 5.5 | 4.6214
10000 | 5.5 | 5.75 | 5.25 | 6.25 | 6.6 | 6.8 | 7 | 6.1643
100000 | 7.5 | 8 | 7 | 7.75 | 7.9 | 8 | 8.25 | 7.7714
1000000 | 8.5 | 8.5 | 8 | 8.25 | 8.75 | 8.9 | 9 | 8.5571
Average | 4.6214 | 4.6429 | 4.3214 | 4.7929 | 4.95 | 5.2071 | 5.45 | 4.8551
Table 8: Total Potential Defects by Type and Size of Software Projects
(Note: Defect potential includes requirements, design, code, document, and bad-fix defect categories)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
10 | 22.5 | 20 | 20 | 25 | 20 | 27 | 29 | 23.3571
100 | 280 | 250 | 250 | 300 | 315 | 330 | 400 | 303.5714
1000 | 4300 | 4250 | 4000 | 4300 | 4750 | 5250 | 5500 | 4621.4286
10000 | 55000 | 57500 | 52500 | 62500 | 66000 | 68000 | 70000 | 61642.8571
100000 | 750000 | 800000 | 700000 | 775000 | 790000 | 800000 | 825000 | 777142.8571
1000000 | 8500000 | 8500000 | 8000000 | 8250000 | 8750000 | 8900000 | 9000000 | 8557142.8571
Average | 1329943.4286 | 1337431.6429 | 1250967.3571 | 1298875.2143 | 1373012.3571 | 1396229.7857 | 1414418.6429 | 1342982.6327
Table 9: Defect Removal Efficiency by Type and Size of Software Projects
(Note: Defect removal activities include inspections and all forms of testing)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 98% | 94% | 99% | 99.5% | 95% | 93% | 98% | 96.64%
10 | 97.5% | 90% | 98% | 99% | 92% | 89% | 96% | 94.5%
100 | 94% | 86% | 96% | 98% | 90% | 87% | 94% | 92.14%
1000 | 85% | 82% | 90% | 96% | 86% | 82% | 92% | 87.57%
10000 | 80% | 74% | 86% | 93% | 84% | 72% | 91% | 82.86%
100000 | 70% | 68% | 80% | 89% | 83% | 70% | 90% | 78.57%
1000000 | 65% | 60% | 77% | 86% | 78% | 60% | 87% | 73.29%
Average | 84.21% | 79.14% | 89.43% | 94.36% | 86.86% | 79% | 92.57% | 86.51%
Table 10: Delivered Defects by Type and Size of Software Projects
(Note: About 25% of delivered defects are of high severity levels)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 0.03 | 0.09 | 0.015 | 0.0075 | 0.075 | 0.105 | 0.03 | 0.050357
10 | 0.5625 | 2 | 0.4 | 0.25 | 1.6 | 2.97 | 1.16 | 1.2775
100 | 16.8 | 35 | 10 | 6 | 31.5 | 42.9 | 24 | 23.7429
1000 | 645 | 765 | 400 | 172 | 665 | 945 | 440 | 576
10000 | 11000 | 14950 | 7350 | 4375 | 10560 | 19040 | 6300 | 10510.7143
100000 | 225000 | 256000 | 140000 | 85250 | 134300 | 240000 | 82500 | 166150
1000000 | 2975000 | 3400000 | 1840000 | 1155000 | 1925000 | 3560000 | 1170000 | 2289285.7143
Average | 458808.9132 | 524536.0129 | 283965.7736 | 177829.0368 | 295794.025 | 545718.7107 | 179895.0271 | 352363.9285
Table 11: Delivered Defects per Function Point by Type and Size of Software Projects
(Note: Most delivered defects will not be found for a number of years.)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 0.03 | 0.09 | 0.015 | 0.0075 | 0.075 | 0.105 | 0.03 | 0.050357
10 | 0.05625 | 0.2 | 0.04 | 0.025 | 0.16 | 0.297 | 0.116 | 0.12775
100 | 0.168 | 0.35 | 0.1 | 0.06 | 0.315 | 0.429 | 0.24 | 0.23743
1000 | 0.645 | 0.765 | 0.4 | 0.172 | 0.665 | 0.945 | 0.44 | 0.576
10000 | 1.1 | 1.495 | 0.735 | 0.4375 | 1.056 | 1.904 | 0.63 | 1.0511
100000 | 2.25 | 2.56 | 1.4 | 0.8525 | 1.343 | 2.4 | 0.825 | 1.6615
1000000 | 2.975 | 3.4 | 1.84 | 1.155 | 1.925 | 3.56 | 1.17 | 2.2893
Average | 1.032 | 1.2657 | 0.64714 | 0.38707 | 0.79129 | 1.3771 | 0.493 | 0.8562
Table 12: Percentage of Delivered Defects found and reported by customers in the first year of application usage
(Note: First year defect reports rise with numbers of users. But excessive delivered defects will slow or stop usage growth.)
(Note: About 25% of first year defect reports are high-severity defects.)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 95% | 97% | 96% | 99% | 95% | 90% | 99% | 95.86%
10 | 92% | 95% | 94% | 96% | 92% | 85% | 96% | 92.86%
100 | 80% | 90% | 85% | 90% | 75% | 70% | 92% | 83.14%
1000 | 55% | 80% | 70% | 85% | 70% | 60% | 82% | 71.71%
10000 | 35% | 60% | 50% | 70% | 55% | 40% | 75% | 55%
100000 | 15% | 40% | 25% | 50% | 35% | 20% | 55% | 34.29%
1000000 | 10% | 30% | 15% | 40% | 25% | 12.5% | 50% | 26.07%
Average | 54.57% | 70.29% | 62.14% | 75.71% | 63.86% | 53.93% | 78.43% | 65.56%
Table 13: Probable Number of Defects found and reported by customers in the first year of application usage
(Note: First year defect reports rise with numbers of users. But excessive delivered defects will slow or stop usage growth.)
(Note: About 25% of first year defect reports are high-severity defects.)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 0.0285 | 0.0873 | 0.0144 | 0.007425 | 0.07125 | 0.0945 | 0.0297 | 0.047582
10 | 0.5175 | 1.9 | 0.376 | 0.24 | 1.472 | 2.5245 | 1.1136 | 1.1634
100 | 13.44 | 31.5 | 8.5 | 5.4 | 23.625 | 30.03 | 22.08 | 19.225
1000 | 354.75 | 612 | 280 | 146.2 | 465.5 | 567 | 360.8 | 398.0357
10000 | 3850 | 8970 | 3675 | 3062.5 | 5808 | 7616 | 4725 | 5386.6429
100000 | 33750 | 102400 | 35000 | 42625 | 47005 | 48000 | 45375 | 50593.5714
1000000 | 297500 | 1020000 | 276000 | 462000 | 481250 | 445000 | 585000 | 509535.7143
Average | 47924.1051 | 161716.4982 | 44994.8415 | 72548.4782 | 76364.8098 | 71602.2356 | 90783.4319 | 80847.7715
Table 14: Probable Number of Defects per Function Point found and reported by customers in the first year of application usage
(Note: First year defect reports rise with numbers of users. But excessive delivered defects will slow or stop usage growth.)
(Note: About 25% of first-year defect reports are high-severity defects.)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 0.0285 | 0.0873 | 0.0144 | 0.007425 | 0.07125 | 0.0945 | 0.0297 | 0.047582
10 | 0.05175 | 0.19 | 0.0376 | 0.024 | 0.1472 | 0.25245 | 0.11136 | 0.11634
100 | 0.1344 | 0.315 | 0.085 | 0.054 | 0.23625 | 0.3003 | 0.2208 | 0.19225
1000 | 0.35475 | 0.612 | 0.28 | 0.1462 | 0.4655 | 0.567 | 0.3608 | 0.39804
10000 | 0.385 | 0.897 | 0.3675 | 0.30625 | 0.5808 | 0.7616 | 0.4725 | 5.0594
100000 | 0.3375 | 1.024 | 0.35 | 0.42625 | 0.47005 | 0.48 | 0.45375 | 0.50594
1000000 | 0.2975 | 1.02 | 0.276 | 0.462 | 0.48125 | 0.445 | 0.585 | 0.50954
Average | 0.22706 | 0.59219 | 0.2015 | 0.20373 | 0.35033 | 0.41441 | 0.31913 | 0.32976
Table 15: Estimated Number of Test Cases Prepared per Function Point for U.S. Software Applications
(Note: Test cases per function point rise with application size, but the sheer volume causes a reduction in coverage with application size)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 2.5 | 2 | 3 | 4 | 3 | 1.5 | 4.25 | 2.8929
10 | 3 | 2.5 | 3.25 | 4.25 | 3.75 | 2 | 4.5 | 3.3214
100 | 3.5 | 3 | 3.75 | 4.75 | 4 | 2.5 | 5 | 3.7857
1000 | 4 | 3.75 | 4.25 | 5 | 4.75 | 3.25 | 5.25 | 4.3214
10000 | 4.5 | 4 | 4.75 | 5.5 | 5.25 | 3.75 | 5.5 | 4.75
100000 | 4 | 3.5 | 4.25 | 5.25 | 5 | 3.25 | 5.75 | 4.4286
1000000 | 3.75 | 3.25 | 4 | 5 | 4 | 2.75 | 5.25 | 4
Average | 3.6071 | 3.1429 | 3.8929 | 4.8214 | 4.25 | 2.7143 | 5.0714 | 3.9286
Table 16: Estimated Number of Test Cases Prepared by Application Size and Type
(Note: To achieve 95% code coverage for testing applications > 10,000 function points in size almost never happens since test cases would approach infinity.)
(Note: Applications > 10,000 function point may use more than 12 kinds of testing. Applications < 1,000 function points seldom use more than 3 kinds of testing.)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 2.5 | 2 | 3 | 4 | 3 | 1.5 | 4.25 | 2.8929
10 | 30 | 25 | 32.5 | 42.5 | 37.5 | 20 | 45 | 33.2143
100 | 350 | 300 | 375 | 475 | 400 | 250 | 500 | 378.5714
1000 | 4000 | 3750 | 4250 | 5000 | 4750 | 3250 | 5250 | 4321.4286
10000 | 45000 | 40000 | 47500 | 55000 | 52500 | 37500 | 55000 | 47500
100000 | 400000 | 350000 | 425000 | 525000 | 500000 | 325000 | 575000 | 442857.1429
1000000 | 3750000 | 3250000 | 4000000 | 5000000 | 4000000 | 2750000 | 5250000 | 4000000
Average | 599911.7857 | 520582.4286 | 639594.3571 | 797931.6429 | 651098.6429 | 445145.9286 | 840828.4643 | 642156.1786
Table 17: Percentage of Development Effort Devoted to Defect Removal, Defect Repair, and Rework
(Note: For applications > 10,000 function points defect removal and repair are the major cost and schedule drivers.)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 10% | 8% | 9% | 7.5% | 12.5% | 15% | 7.5% | 9.929%
10 | 15% | 12.5% | 12.5% | 12.5% | 15% | 17.5% | 12.5% | 13.93%
100 | 20% | 15% | 17.5% | 15% | 20% | 22.5% | 15% | 17.86%
1000 | 30% | 25% | 25% | 20% | 22.5% | 35% | 22.5% | 25.71%
10000 | 40% | 35% | 35% | 25% | 37.5% | 45% | 27.5% | 35%
100000 | 45% | 40% | 40% | 30% | 40% | 55% | 35% | 40.71%
1000000 | 50% | 45% | 47.5% | 40% | 45% | 60% | 42.5% | 47.14%
Average | 30% | 25.79% | 26.64% | 21.43% | 27.5% | 35.71% | 23.21% | 27.18%
Table 18: Estimated Number of Calendar Years after Delivery for Software Applications to Stabilize and approach Zero Defects
(Note: Due to bad-fix injections and error-prone modules, zero defect status does not occur above 1000 function points)
(Note: Above 10,000 function points the stabilization period is longer than the life expectancy of the applications.)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 0.23154 | 0.26428 | 0.1884 | 0.118 | 0.28455 | 0.35873 | 0.1612 | 0.22953
10 | 0.49771 | 0.59566 | 0.43206 | 0.35481 | 0.62968 | 0.83366 | 0.50115 | 0.54925
100 | 1.3135 | 1.3256 | 1.0955 | 0.89142 | 1.5909 | 1.7769 | 1.1581 | 1.3074
1000 | 3.582 | 3.1014 | 2.9364 | 2.0779 | 3.2922 | 3.8013 | 2.6743 | 3.0665
10000 | 7.3658 | 7.0755 | 6.3414 | 5.0301 | 6.7189 | 8.1848 | 5.2407 | 6.5653
100000 | 15.4298 | 14.6872 | 13.4824 | 11.0071 | 12.9337 | 15.4434 | 10.6703 | 13.3791
1000000 | 27.9408 | 27.2101 | 24.7573 | 20.6141 | 24.3156 | 28.9087 | 19.8431 | 24.7985
Average | 8.0516 | 7.7514 | 7.0334 | 5.7276 | 7.1094 | 8.4725 | 5.7498 | 7.128
Table 19: Estimated Number of U.S. Software Projects in Progress Circa 2008
(Note: Both new development projects and maintenance and enhancement projects are included.)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Total
Size in FP
1 | 100000 | 200000 | 70000 | 75000 | 60000 | 55000 | 70000 | 630000
10 | 75000 | 100000 | 40000 | 25000 | 25000 | 20000 | 35000 | 320000
100 | 25000 | 60000 | 12500 | 10000 | 10000 | 7500 | 6500 | 131500
1000 | 10000 | 35000 | 7000 | 5000 | 5000 | 4000 | 4500 | 70500
10000 | 2000 | 7500 | 1750 | 3000 | 2500 | 2000 | 3000 | 21750
100000 | 10 | 5 | 5 | 25 | 5 | 60 | 75 | 185
1000000 | 2.975e-06 | 3.4e-06 | 1.84e-06 | 2 | 3 | 5 | 20 | 30
Total | 212010 | 402505 | 131255 | 118027 | 102508 | 88565 | 119095 | 1173965
Table 20: Estimated Number of U.S. Software Engineers, Specialists, and Managers Circa 2008
(Note: More than 90 kinds of specialists are employed in the overall U.S. software industry.)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Total
Size in FP
1 | 10000 | 20000 | 7000 | 7500 | 6000 | 5500 | 7000 | 63000
10 | 18750 | 25000 | 10000 | 6250 | 6250 | 5000 | 8750 | 80000
100 | 33333.3333 | 92307.6923 | 16666.6667 | 14285.7143 | 14084.507 | 12500 | 11403.5088 | 194581.4224
1000 | 58823.5294 | 201149.4253 | 42424.2424 | 30487.8049 | 31645.5696 | 25806.4516 | 31690.1408 | 422027.1641
10000 | 123456.7901 | 446428.5714 | 106707.3171 | 187500 | 160256.4103 | 129032.2581 | 200000 | 1353381.3469
100000 | 6329.1139 | 3125 | 3086.4198 | 16025.641 | 3144.6541 | 38961.039 | 50675.6757 | 121347.5434
1000000 | 0.019071 | 0.020859 | 0.011646 | 12903.2258 | 19607.8431 | 32894.7368 | 135135.1351 | 200540.9925
Total | 250692.7859 | 788010.7099 | 185884.6576 | 274952.386 | 240988.9841 | 249694.4855 | 444654.4604 | 2434878.4694
Table 21: Estimated Percentage of Projects Cancelled due to Poor Quality or Excessive Overruns
(Note: Cancellation rates are directly proportional to application size. Projects > 10,000 function points are extremely hazardous.)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 1% | 1% | 1% | 1% | 1% | 1% | 1% | 1%
10 | 2% | 2% | 2% | 1% | 2% | 2% | 2% | 1.857%
100 | 3% | 2.5% | 2.5% | 1.5% | 2% | 5% | 6% | 3.214%
1000 | 10% | 12% | 8% | 5% | 9% | 13% | 14% | 10.14%
10000 | 32% | 36% | 24% | 17% | 26% | 40% | 44% | 31.29%
100000 | 52% | 55% | 46% | 30% | 33% | 57% | 60% | 47.57%
1000000 | 95% | 97% | 78% | 62% | 66% | 96% | 82% | 82.29%
Average | 27.86% | 29.36% | 23.07% | 16.79% | 19.86% | 30.57% | 29.86% | 25.34%
Table 22: Estimated U.S. Software Staff Working on Projects that will be Cancelled due to Poor Quality or Excessive Overruns
(Note: Cancellation rates are directly proportional to application size. Projects > 10,000 function points are extremely hazardous.)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Total
Size in FP
1 | 100 | 200 | 70 | 75 | 60 | 55 | 70 | 630
10 | 375 | 500 | 200 | 62.5 | 125 | 100 | 175 | 1537.5
100 | 1000 | 2307.6923 | 416.6667 | 214.2857 | 281.6901 | 625 | 684.2105 | 5529.5454
1000 | 5882.3529 | 24137.931 | 3393.9394 | 1524.3902 | 2848.1013 | 3354.8387 | 4436.6197 | 45578.1733
10000 | 39506.1728 | 160714.2857 | 25609.7561 | 31875 | 41666.6667 | 51612.9032 | 88000 | 438984.7845
100000 | 3291.1392 | 1718.75 | 1419.7531 | 4807.6923 | 1037.7358 | 22207.7922 | 30405.4054 | 64888.2681
1000000 | 0.018117 | 0.020233 | 0.0090835 | 8000 | 12941.1765 | 31578.9474 | 110810.8108 | 163330.9821
Total | 50154.6831 | 189578.6793 | 31110.1243 | 46558.8683 | 58960.3704 | 109534.4815 | 234582.0465 | 720479.2534
Table 23: Estimated Average Cost for Cancelled U.S. Software Projects
(Note: Cancelled projects are usually 15% late and over budget at the point of cancellation; often more; seldom less.)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 107.25 | 149.73 | 105.57 | 151.875 | 110.88 | 122.605 | 157.8375 | 129.3925
10 | 3822 | 3885.85 | 3580.5825 | 9072 | 7902.72 | 11063.745 | 15852.375 | 7882.7532
100 | 59280 | 73713.2308 | 51318.75 | 99369.6429 | 64739.1549 | 113879.7917 | 195015.3947 | 93902.2807
1000 | 791470.5882 | 926080.4598 | 739641.6667 | 1325304.878 | 953772.1519 | 1212750 | 2018154.9296 | 1138167.8106
10000 | 31248148.1481 | 36116845.2381 | 29164070.122 | 40647656.25 | 32023384.6154 | 38076500 | 52045200 | 37045972.0534
100000 | 443810126.5823 | 561487500 | 400714660.4938 | 569725961.5385 | 426529811.3208 | 517101136.3636 | 719171452.7027 | 519791521.286
1000000 | 5226250000 | 6543852760.7362 | 4763765822.7848 | 6662903225.8065 | 5150484705.8824 | 6319411184.2105 | 8435310810.8108 | 6157425501.4616
Average | 814594707.7955 | 1020351562.1778 | 742062742.8528 | 1039244391.713 | 801437775.2465 | 982275233.8165 | 1315536663.4358 | 959357582.434
Table 24: Estimated Average Cost per Function Point for Cancelled U.S. Software Projects
(Note: Cancelled projects cost more than completed projects of the same size and type.)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 107.25 | 149.73 | 105.57 | 151.875 | 110.88 | 122.605 | 157.8375 | 129.3925
10 | 382.2 | 388.585 | 358.0583 | 907.2 | 790.272 | 1106.3745 | 1585.2375 | 788.2753
100 | 592.8 | 737.1323 | 513.1875 | 993.6964 | 647.3915 | 1138.7979 | 1950.1539 | 939.0228
1000 | 791.4706 | 926.0805 | 739.6417 | 1325.3049 | 953.7722 | 1212.75 | 2018.1549 | 1138.1678
10000 | 3124.8148 | 3611.6845 | 2916.407 | 4064.7656 | 3202.3385 | 3807.65 | 5204.52 | 3704.5972
100000 | 4438.1013 | 5614.875 | 4007.1466 | 5697.2596 | 4265.2981 | 5171.0114 | 7191.7145 | 5197.9152
1000000 | 5226.25 | 6543.8528 | 4763.7658 | 6662.9032 | 5150.4847 | 6319.4112 | 8435.3108 | 6157.4255
Average | 2094.6981 | 2567.42 | 1914.8253 | 2829.0007 | 2160.0624 | 2696.9429 | 3791.847 | 2579.2566
Table 25: Percentage of U.S. Software Staff Working on Projects that will be Cancelled due to Poor Quality or Excessive Overruns
(Note: At any given period about one third of U.S. software personnel are working on projects that will never be completed.)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Total
Total staff | 250692.7859 | 788010.7099 | 185884.6576 | 274952.386 | 240988.9841 | 249694.4855 | 444654.4604 | 2434878.4694
Cancelled staff | 50154.6831 | 189578.6793 | 31110.1243 | 46558.8683 | 58960.3704 | 109534.4815 | 234370.3071 | 720267.5141
Difference | 200538.1027 | 598432.0306 | 154774.5332 | 228393.5177 | 182028.6138 | 140160.004 | 210284.1533 | 1714610.9553
Percent | 20.01% | 24.06% | 16.74% | 16.93% | 24.47% | 43.87% | 52.71% | 29.58%
Table 26: Costs of Cancelled Projects as a percentage of Costs of Completed Projects of the same size and type
(Note: Because most cancelled projects are late and overbudget, they cost substantially more than successful projects of the same size)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 110% | 105% | 108% | 112.5% | 110% | 113% | 115% | 110.5%
10 | 112% | 109% | 111% | 112% | 112% | 113.3% | 115.5% | 112.1%
100 | 114% | 109% | 112.5% | 114.5% | 114% | 114.5% | 115.7% | 113.5%
1000 | 115% | 113% | 113.5% | 115% | 115% | 115.5% | 116% | 114.7%
10000 | 118% | 115% | 116.5% | 117.5% | 118% | 118.3% | 118.5% | 117.4%
100000 | 116% | 112.5% | 114.5% | 115.5% | 116% | 116.5% | 117.5% | 115.5%
1000000 | 113% | 110% | 110% | 112.5% | 113.3% | 113.5% | 113.7% | 112.3%
Average | 114% | 110.5% | 112.3% | 114.2% | 114% | 114.9% | 116% | 113.7%
Table 27: Estimated Percentage of U.S. Maintenance and Enhancement Projects
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 99% | 99% | 99% | 99% | 99% | 99% | 99% | 99%
10 | 99% | 95% | 95% | 93% | 97% | 98% | 92% | 95.57%
100 | 85% | 65% | 80% | 74% | 80% | 85% | 78% | 78.14%
1000 | 60% | 45% | 55% | 58% | 59% | 62% | 64% | 57.57%
10000 | 48% | 33% | 42% | 47% | 51% | 52% | 54% | 46.71%
100000 | 40% | 18% | 37% | 40% | 44% | 45% | 48% | 38.86%
1000000 | 16% | 10% | 12% | 18% | 26% | 24% | 33% | 19.86%
Average | 63.86% | 52.14% | 60% | 61.29% | 65.14% | 66.43% | 66.86% | 62.24%
Table 28: Estimated Number of U.S. Staff Working on Maintenance and Enhancement Projects
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Total
Size in FP
1 | 9900 | 19800 | 6930 | 7425 | 5940 | 5445 | 6930 | 62370
10 | 18562.5 | 23750 | 9500 | 5812.5 | 6062.5 | 4900 | 8050 | 76637.5
100 | 28333.3333 | 60000 | 13333.3333 | 10571.4286 | 11267.6056 | 10625 | 8894.7368 | 143025.4377
1000 | 35294.1176 | 90517.2414 | 23333.3333 | 17682.9268 | 18670.8861 | 16000 | 20281.6901 | 221780.1954
10000 | 59259.2593 | 147321.4286 | 44817.0732 | 88125 | 81730.7692 | 67096.7742 | 108000 | 596350.3044
100000 | 2531.6456 | 562.5 | 1141.9753 | 6410.2564 | 1383.6478 | 17532.4675 | 24324.3243 | 53886.8169
1000000 | 0.0030513 | 0.0020859 | 0.0013975 | 2322.5806 | 5098.0392 | 7894.7368 | 44594.5946 | 59909.9578
Total | 135383.5286 | 341951.172 | 99055.7165 | 138349.6925 | 130153.448 | 129493.9786 | 221075.3459 | 1213960.2123
Table 29: Estimated Distribution of U.S. Software Staff between New and Maintenance and Enhancement Projects
(Note: For older forms of software maintenance and enhancement workers outnumber development workers. For web application, the reverse is true.)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Total
New Projects | 115309.2573 | 446059.5378 | 86828.941 | 136602.6935 | 110835.5362 | 120200.5069 | 223579.1145 | 1220918.257
M&E Projects | 135383.5286 | 341951.172 | 99055.7165 | 138349.6925 | 130153.448 | 129493.9786 | 221075.3459 | 1213960.2123
Total staff | 250692.7859 | 788010.7099 | 185884.6576 | 274952.386 | 240988.9841 | 249694.4855 | 444654.4604 | 2434878.4694
Development % | 46% | 56.61% | 46.71% | 49.68% | 45.99% | 48.14% | 50.28% | 50.14%
Maintenance % | 54% | 43.39% | 53.29% | 50.32% | 54.01% | 51.86% | 49.72% | 49.86%
Table 30: Probability of Serious Security Vulnerabilities in Software Applications
(Note: security vulnerabilities and poor quality are both common software problems circa 2008)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 10% | 12% | 7% | 5% | 15% | 25% | 5% | 11.29%
10 | 30% | 35% | 22% | 15% | 30% | 35% | 15% | 26%
100 | 40% | 40% | 30% | 20% | 40% | 45% | 20% | 33.57%
1000 | 70% | 65% | 55% | 40% | 60% | 62% | 30% | 54.57%
10000 | 96% | 80% | 80% | 70% | 77% | 80% | 35% | 74%
100000 | 97% | 87% | 90% | 75% | 85% | 87% | 40% | 80.14%
1000000 | 98% | 92% | 91% | 90% | 96% | 92% | 45% | 86.29%
Average | 63% | 58.71% | 53.57% | 45% | 57.57% | 60.86% | 27.14% | 52.27%
Table 31: Estimated Number of Security Vulnerabilities in Software Applications
(Note: For applications running on computers connected to the web, security vulnerabilities approach 100%)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
10 | 5.0119 | 5.2481 | 4.8978 | 4.4668 | 5.3088 | 5.3703 | 3.8019 | 4.8722
100 | 25.1189 | 27.5423 | 23.9883 | 19.9526 | 28.1838 | 28.8403 | 14.4544 | 24.0115
1000 | 125.8925 | 144.544 | 117.4898 | 89.1251 | 149.6236 | 154.8817 | 54.9541 | 119.5015
10000 | 630.9573 | 758.5776 | 575.4399 | 398.1072 | 794.3282 | 831.7638 | 208.9296 | 599.7291
100000 | 3162.2777 | 3981.0717 | 2818.3829 | 1778.2794 | 4216.965 | 4466.8359 | 794.3282 | 3031.163
1000000 | 15848.9319 | 20892.9613 | 13803.8426 | 7943.2823 | 22387.2114 | 23988.3292 | 3019.9517 | 15412.0729
Average | 2828.4557 | 3687.2778 | 2477.8631 | 1462.0305 | 3940.3744 | 4211.003 | 585.3457 | 2741.7643
Table 32: Probability of Data Theft or Security Attack within Five Years of Deployment
(Note: the odds of Identify theft and loss of proprietary and confidential data appear to the be growing rapidly.)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 1% | 2% | 7% | 5% | 10% | 12% | 5% | 6%
10 | 3% | 5% | 2% | 1% | 10% | 13% | 15% | 7%
100 | 5% | 12% | 4% | 3% | 10% | 15% | 20% | 9.857%
1000 | 12% | 20% | 10% | 7% | 15% | 20% | 23% | 15.29%
10000 | 25% | 30% | 20% | 17% | 26% | 28% | 25% | 24.43%
100000 | 22% | 25% | 15% | 14% | 24% | 22% | 10% | 18.86%
1000000 | 20% | 30% | 15% | 12% | 17% | 20% | 5% | 17%
Average | 12.57% | 17.71% | 10.43% | 8.429% | 16% | 18.57% | 14.71% | 14.06%
Table 33: Estimated Life Expectancy of Applications before Retirement or Replacement
(Note: Data is expressed in terms of calendar years from first deployment until last retirement. Length of service is proportional to size.)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 1.4 | 1 | 1.5 | 3 | 2 | 2 | 3 | 1.9857
10 | 2.5 | 2 | 3 | 4 | 3 | 4 | 4 | 3.2143
100 | 4 | 3 | 4.5 | 4.5 | 4 | 5.5 | 5 | 4.3571
1000 | 5 | 4 | 5 | 6 | 5 | 8 | 9 | 6
10000 | 18 | 9 | 14 | 13 | 9 | 22 | 23 | 15.4286
100000 | 20 | 10 | 17 | 15 | 14 | 24 | 24 | 17.7143
1000000 | 25 | 12 | 27 | 18 | 20 | 28 | 26 | 22.2857
Average | 10.8429 | 5.8571 | 10.2857 | 9.0714 | 8.1429 | 13.3571 | 13.4286 | 10.1408
Table 34: Estimated Rate of Annual Software Application Growth and Change After Deployment
(Note: Data is expressed as a percentage of the original size of the application in function points)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 3% | 6% | 3% | 4% | 6% | 5% | 5% | 4.571%
10 | 4% | 7% | 3% | 4% | 7% | 5% | 6% | 5.143%
100 | 5% | 9% | 4% | 5% | 8% | 6% | 8% | 6.429%
1000 | 8% | 8% | 5% | 6% | 10% | 8% | 9% | 7.714%
10000 | 7% | 10% | 6% | 5% | 9% | 9% | 8% | 7.714%
100000 | 3.5% | 5% | 3% | 4% | 7% | 8% | 9% | 5.643%
1000000 | 2% | 2.5% | 1.75% | 3% | 3.5% | 3.75% | 4% | 2.929%
Average | 4.643% | 6.786% | 3.679% | 4.429% | 7.214% | 6.393% | 7% | 5.735%
Table 35: Estimated Number of Function Points Added or Changed After Deployment on an Annual Basis
(Note: Software that is in active use grows throughout its lifetime.)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 0.03 | 0.06 | 0.03 | 0.04 | 0.06 | 0.05 | 0.05 | 0.029286
10 | 0.4 | 0.7 | 0.3 | 0.4 | 0.7 | 0.5 | 0.6 | 0.057347
100 | 5 | 9 | 4 | 5 | 8 | 6 | 8 | 6.4286
1000 | 80 | 80 | 50 | 60 | 100 | 80 | 90 | 77.1429
10000 | 700 | 1000 | 600 | 500 | 900 | 900 | 800 | 771.4286
100000 | 3500 | 5000 | 3000 | 4000 | 7000 | 8000 | 9000 | 5642.8571
1000000 | 20000 | 25000 | 17500 | 30000 | 35000 | 37500 | 40000 | 29285.7143
Average | 3469.3471 | 4441.3943 | 3022.0471 | 4937.92 | 6144.1086 | 6640.9357 | 7128.3786 | 5112.0188
Table 36: Estimated Total Growth in Function Points from Deployment until Retirement of Software Applications
(Note: This table is the combined results of tables 33, 34, and 35)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 0.042 | 0.06 | 0.045 | 0.12 | 0.12 | 0.1 | 0.15 | 0.091
10 | 1 | 1.4 | 0.9 | 1.6 | 2.1 | 2 | 2.4 | 1.6286
100 | 20 | 27 | 18 | 22.5 | 32 | 33 | 40 | 27.5
1000 | 400 | 320 | 250 | 360 | 500 | 640 | 810 | 468.5714
10000 | 12600 | 9000 | 8400 | 6500 | 8100 | 19800 | 18400 | 11828.5714
100000 | 70000 | 50000 | 51000 | 60000 | 98000 | 192000 | 216000 | 105285.7143
1000000 | 500000 | 300000 | 472500 | 540000 | 700000 | 1050000 | 1040000 | 657500
Average | 83288.7203 | 51335.4943 | 76024.135 | 86697.7457 | 115233.46 | 180353.5857 | 182178.9357 | 110730.2967
Table 37: Estimated percent of Aging Software Applications with Structural Decay, Error-prone Modules, and Geriatic Problems
(Note: As software applications age structural complexity increases and bad-fix injections increase. Decay is proportional to application size)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 10% | 7% | 6% | 5% | 5% | 12% | 5% | 7.143%
10 | 12% | 13% | 9% | 7% | 10% | 15% | 7% | 10.43%
100 | 18% | 20% | 12% | 10% | 15% | 20% | 9% | 14.86%
1000 | 35% | 35% | 25% | 15% | 20% | 25% | 12% | 23.86%
10000 | 55% | 40% | 35% | 25% | 37% | 60% | 25% | 39.57%
100000 | 75% | 45% | 50% | 30% | 45% | 78% | 30% | 50.43%
1000000 | 85% | 50% | 55% | 40% | 55% | 88% | 35% | 58.29%
Average | 41.43% | 30% | 27.43% | 18.86% | 26.71% | 42.57% | 17.57% | 29.22%
Table 38: Estimated Number of Legacy Applications in service for > 5 years as of 2008
(Note: Large applications have longer service lives than small applications because replacement is so expensive at above 10,000 function points)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Total
Size in FP
1 | 5000 | 10000 | 3500 | 3750 | 3000 | 2750 | 3500 | 31500
10 | 7500 | 10000 | 4000 | 2500 | 2500 | 2000 | 3500 | 32000
100 | 3000 | 7200 | 1500 | 1200 | 1200 | 900 | 780 | 15780
1000 | 15000 | 52500 | 10500 | 7500 | 7500 | 6000 | 6750 | 105750
10000 | 4000 | 15000 | 3500 | 6000 | 5000 | 4000 | 6000 | 43500
100000 | 40 | 20 | 20 | 100 | 20 | 105 | 187.5 | 492.5
1000000 | 1.4875e-05 | 1.7e-05 | 9.2e-06 | 10 | 15 | 12.75 | 55 | 92.75
Total | 34540 | 94720 | 23020 | 21060 | 19235 | 15767.75 | 20772.5 | 229115.25
Table 39: Estimated Percentage of Legacy Applications that have been fully Renovated
(Note: Full renovation includes restructuring, refactoring, data mining of business rules, function point analysis of size, removal of error-prone modules)
(Note: Both the value and the difficulty of renovation increase as application size increases.)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 15% | 15% | 15% | 20% | 17.5% | 15% | 17% | 16.36%
10 | 12.5% | 10% | 12.5% | 15% | 12.5% | 10% | 12.5% | 12.14%
100 | 10% | 10% | 12% | 13.5% | 14.5% | 9% | 11.5% | 11.5%
1000 | 12.5% | 13% | 13.3% | 14% | 15.5% | 7.5% | 15.5% | 13.04%
10000 | 7% | 8% | 8.5% | 9.75% | 9.5% | 6% | 9.5% | 8.321%
100000 | 6% | 6% | 6% | 8% | 7% | 4% | 6% | 6.143%
1000000 | 2% | 5% | 5% | 5% | 6% | 1% | 3% | 3.857%
Average | 3% | 3% | 4% | 5% | 11.79% | 7.5% | 10.71% | 6.429%
Table 40: Estimated Number of Aging Legacy Applications that have been fully renovated as of 2008
(Note: Full renovation includes restructuring, refactoring, data mining of business rules, function point analysis of size, removal of error-prone modules)
(Note: Both the value and the difficulty of renovation increase as application size increases.)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Total
Size in FP
1 | 750 | 1500 | 525 | 750 | 525 | 412.5 | 595 | 5057.5
10 | 937.5 | 1250 | 500 | 375 | 312.5 | 200 | 437.5 | 4012.5
100 | 300 | 720 | 180 | 162 | 174 | 81 | 89.7 | 1706.7
1000 | 1875 | 6825 | 1396.5 | 1050 | 1162.5 | 450 | 1046.25 | 13805.25
10000 | 280 | 1200 | 297.5 | 585 | 475 | 240 | 570 | 3647.5
100000 | 2.4 | 1.2 | 1.2 | 8 | 1.4 | 6.3 | 11.25 | 31.75
1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 4144.9 | 11496.2 | 2900.2 | 2930 | 2650.4 | 1389.8 | 2749.7 | 28261.2
Table 41: Approximate Monthly Percent Increase in Requirements Creep and Churn during development
(Note: Requirements creep and churn run from the end of the requirements phase through the design and code phases)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 1% | 1.25% | 0.9% | 0.9% | 1.2% | 1.25% | 1.3% | 1.114%
10 | 1.05% | 1.3% | 1% | 1% | 1.5% | 1.2% | 1.35% | 1.2%
100 | 1.15% | 1.5% | 1.05% | 1.1% | 1.8% | 1.3% | 1.4% | 1.329%
1000 | 1.2% | 2.25% | 1.1% | 1.2% | 2% | 1.7% | 1.8% | 1.607%
10000 | 1.4% | 1.75% | 1.3% | 1.4% | 1.75% | 2% | 1.5% | 1.586%
100000 | 1.2% | 1.5% | 1.05% | 1.6% | 1.5% | 1.5% | 1.65% | 1.429%
1000000 | 1.1% | 1.25% | 0.95% | 1.35% | 1.3% | 1.4% | 1.4% | 1.25%
Average | 1.157% | 1.543% | 1.05% | 1.221% | 1.579% | 1.479% | 1.486% | 1.359%
Table 42: Approximate Total Percent Growth due to Requirements Creep and Churn from initiation to deployment
(Note: Requirements creep runs from the end of the requirements phase through the design and code phases)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 0.005% | 0.00625% | 0.0045% | 0.0045% | 0.006% | 0.00625% | 0.0065% | 0.005571%
10 | 0.1837% | 0.1625% | 0.165% | 0.3% | 0.525% | 0.54% | 0.675% | 0.3645%
100 | 2.3% | 2.25% | 1.838% | 2.475% | 3.6% | 3.575% | 4.9% | 2.991%
1000 | 7.2% | 11.25% | 6.05% | 8.4% | 13% | 12.75% | 16.2% | 10.69%
10000 | 30.8% | 32.38% | 27.3% | 28.7% | 36.75% | 46% | 36% | 33.99%
100000 | 37.2% | 42% | 30.45% | 45.6% | 43.5% | 47.25% | 54.45% | 42.92%
1000000 | 40.7% | 42.5% | 33.25% | 45.9% | 44.85% | 54.6% | 56% | 45.4%
Average | 16.91% | 18.65% | 14.15% | 18.77% | 20.32% | 23.53% | 24.03% | 19.48%
Table 43: Approximate Growth in Function Points due to Requirements Creep and Churn from initiation to deployment
(Note: The starting sizes of this table are the nominal sizes in the left column. The results are the additional function points due to creep and churn.)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 5e-05 | 6.25e-05 | 4.5e-05 | 4.5e-05 | 6e-05 | 6.25e-05 | 6.5e-05 | 5.5714e-05
10 | 0.018375 | 0.01625 | 0.0165 | 0.03 | 0.0525 | 0.054 | 0.0675 | 0.036446
100 | 2.3 | 2.25 | 1.8375 | 2.475 | 3.6 | 3.575 | 4.9 | 2.9911
1000 | 72 | 112.5 | 60.5 | 84 | 130 | 127.5 | 162 | 106.9286
10000 | 3080 | 3237.5 | 2730 | 2870 | 3675 | 4600 | 3600 | 3398.9286
100000 | 37200 | 42000 | 30450 | 45600 | 43500 | 47250 | 54450 | 42921.4286
1000000 | 407000 | 425000 | 332500 | 459000 | 448500 | 546000 | 560000 | 454000
Average | 63907.7598 | 67193.1809 | 52248.9077 | 72508.0721 | 70829.8075 | 85425.8756 | 88316.7097 | 71490.0448
Table 44: Approximate Size at Deployment of Orignal Requirements plus Requirements Creep and Churn
(Note: The size of the project at the end of the requirements phase is shown by the values in the left column.)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 1.0001 | 1.0001 | 1 | 1 | 1.0001 | 1.0001 | 1.0001 | 1.0001
10 | 10.0184 | 10.0162 | 10.0165 | 10.03 | 10.0525 | 10.054 | 10.0675 | 10.0364
100 | 102.3 | 102.25 | 101.8375 | 102.475 | 103.6 | 103.575 | 104.9 | 102.9911
1000 | 1072 | 1112.5 | 1060.5 | 1084 | 1130 | 1127.5 | 1162 | 1106.9286
10000 | 13080 | 13237.5 | 12730 | 12870 | 13675 | 14600 | 13600 | 13398.9286
100000 | 137200 | 142000 | 130450 | 145600 | 143500 | 147250 | 154450 | 142921.4286
1000000 | 1407000 | 1425000 | 1332500 | 1459000 | 1448500 | 1546000 | 1560000 | 1454000
Average | 222637.9026 | 225923.3238 | 210979.0506 | 231238.215 | 229559.9504 | 244156.0184 | 247046.8525 | 230220.1876
Table 45: Approximate percentage of U.S. Software Applications using technologies which lead to successful development and deployment
(Note: Successful technologies include formal estimates, formal inspections, formal change control, formal tracking, CMM 3 or higher, TSP/PSP, project offices,
six-sigma for software, renovation of legacy applications, removal of error-prone modules, formal measurements, daily SCRUM sessions and full testing)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 60% | 70% | 75% | 95% | 80% | 55% | 92.5% | 75.36%
10 | 55% | 65% | 70% | 90% | 70% | 50% | 90% | 70%
100 | 50% | 60% | 65% | 85% | 60% | 45% | 82.5% | 63.93%
1000 | 35% | 55% | 60% | 80% | 55% | 25% | 75% | 55%
10000 | 15% | 35% | 55% | 70% | 35% | 12.5% | 65% | 41.07%
100000 | 5% | 20% | 40% | 55% | 25% | 10% | 45% | 28.57%
1000000 | 2.5% | 15% | 25% | 40% | 20% | 1.5% | 30% | 19.14%
Average | 31.79% | 45.71% | 55.71% | 73.57% | 49.29% | 28.43% | 68.57% | 50.44%
Table 46: Approximate percent of reused components and source code in U.S. Software Applications
(Note: Reuse includes requirements, architecture, designs, source code, test cases, and user guides)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 55% | 92.5% | 65% | 75% | 85% | 50% | 72.5% | 70.71%
10 | 50% | 87.5% | 60% | 70% | 82.5% | 45% | 70% | 66.43%
100 | 40% | 85% | 55% | 65% | 80% | 37.5% | 62.5% | 60.71%
1000 | 25% | 75% | 50% | 62.5% | 65% | 22.5% | 57.5% | 51.07%
10000 | 20% | 50% | 45% | 50% | 50% | 15% | 45% | 39.29%
100000 | 12.5% | 35% | 25% | 35% | 35% | 12.5% | 32.5% | 26.79%
1000000 | 10% | 30% | 20% | 32.5% | 30% | 7.5% | 30% | 22.86%
Average | 30.36% | 65% | 45.71% | 55.71% | 61.07% | 27.14% | 52.86% | 48.27%
Table 47: Approximate volume of reused function points in U.S. software applications
(Note: Successful reuse requires a certified source for reusable components and near zero-defect quality levels)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | Average
Size in FP
1 | 0.55 | 0.925 | 0.65 | 0.75 | 0.85 | 0.5 | 0.725 | 0.70714
10 | 5 | 8.75 | 6 | 7 | 8.25 | 4.5 | 7 | 6.6429
100 | 40 | 85 | 55 | 65 | 80 | 37.5 | 62.5 | 60.7143
1000 | 250 | 750 | 500 | 625 | 650 | 225 | 575 | 510.7143
10000 | 2000 | 5000 | 4500 | 5000 | 5000 | 1500 | 4500 | 3928.5714
100000 | 12500 | 35000 | 25000 | 35000 | 35000 | 12500 | 32500 | 26785.7143
1000000 | 100000 | 300000 | 200000 | 325000 | 300000 | 75000 | 300000 | 228571.4286
Average | 16399.3643 | 48692.0964 | 32865.95 | 52242.5357 | 48677.0143 | 12752.5 | 48235.0321 | 37123.499
Table 48: Approximate Numbers of projects examined for tables 1-47 and years covered by the projects
(Note: Non-disclosure agreements with clients preclude identifying actual sources of data.)
|  |  | Domestic | Systems & |  | Civilian
| MIS | Web | Outsource | Embedded | Commercial | Government | Military
| Projects | Projects | Projects | Projects | Projects | Projects | Projects | TOTAL
Number of | 5000 | 850 | 2400 | 2550 | 1650 | 350 | 250 | 13050
Projects
Considered
Number of | 450 | 50 | 350 | 300 | 250 | 50 | 50 | 1500
Fully Measured
Projects
Years:
Earliest Year | 1973 | 2000 | 1983 | 1973 | 1973 | 1977 | 1984 | 1973
Latest Year | 2008 | 2008 | 2008 | 2008 | 2008 | 2008 | 2008 | 2008
Range of years | 35 | 8 | 25 | 35 | 35 | 31 | 24 | 27.5714
On-going | 212010 | 402505 | 131255 | 118027 | 102508 | 88565 | 119095 | 1173965
U.S.Projects
in 2008
(estimated)
Legacy | 34540 | 94720 | 23020 | 21060 | 19235 | 15767.75 | 20772.5 | 229115.25
Applications
in 2008
(estimated)
Total U.S. | 246550 | 497225 | 154275 | 139087 | 121743 | 104332.75 | 139867.5 | 1403080.25
Applications
in 2008
(estimated)
Sample Size | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5%
Needed for
Accuracy | 12327.5 | 24861.25 | 7713.75 | 6954.35 | 6087.15 | 5216.6375 | 6993.375 | 70154.0125
Probable | Low | Very Low | Low | Low | Low | Very Low | Very Low | Very Low
Accuracy of
Current Tables
Table 49: | Predicted Function Point Sizes for 150 Sample Applications
Note 1: The sizes shown in table 49 are predicted sizes using the Software Risk Master sizing algorithms.
Note 2: The sizes are set to match the assumptions of IFPUG function point metrics, version 4.2 of the counting rules.
Copyright©2008 by Capers Jones & Associates LLC.
| Capers Jones |  |  | 2008-03-12
| Application |  |  | Size in
Function Points
(IFPUG 4.2)
(Note: Applications larger than 100,000 function points include major defense systems, large ERP applications,
and large operating systems. Such applications are important, expensive, and hazardous to construct.
Once constructed, they have very long life expectancies because replacement is too costly and time consuming.
Such applications never use standard function point analysis since the costs and schedules would be too great.)
1 | Star Wars missile defense |  |  | 352330
2 | Oracle |  |  | 310346
3 | WWMCCS |  |  | 307328
4 | U.S. Air Traffic control |  |  | 306324
5 | Israeli air defense system |  |  | 300655
6 | SAP |  |  | 296764
7 | NSA Echelon |  |  | 293388
8 | North Korean Border defenses |  |  | 273961
9 | Iran's air defense system |  |  | 260100
10 | Aegis destroyer C&C |  |  | 253088
11 | Microsoft VISTA |  |  | 157658
12 | Microsoft XP |  |  | 126788
13 | IBM MVS |  |  | 104738
(Note: Applications between 10,000 and 100,000 function points comprise the main applications that drive
business and government operations. Such applications are important, expensive, and difficult to construct.
Also in this size range are systems and embedded software for complex equipment and weapons systems.
Few applications in this size range use normal IFPUG function points due to the high cost of normal
function point analysis. The values shown here are predicted values from the Software Risk Master tool.)
14 | Microsoft Office Professional |  |  | 93498
15 | Airline reservation system |  |  | 38392
16 | NSA code decryption |  |  | 35897
17 | FBI Carnivore |  |  | 31111
18 | Brain/Computer interface |  |  | 25327
19 | FBI fingerprint analysis |  |  | 25075
20 | NASA space shuttle |  |  | 23153
21 | VA Patient monitoring |  |  | 23109
22 | F115 avionics package |  |  | 22481
23 | LexisNexis Legal analysis |  |  | 22434
24 | Russian weather satellite |  |  | 22278
25 | Data Warehouse |  |  | 21895
26 | Animated film graphics |  |  | 21813
27 | NASA Hubble controls |  |  | 21632
28 | Skype |  |  | 21202
29 | Shipboard gun controls |  |  | 21199
30 | Natural language translation |  |  | 20350
31 | American Express billing |  |  | 20141
32 | M1 Abrams battle tank |  |  | 19569
33 | Boeing 747 avionics package |  |  | 19446
34 | NASA Mars rover |  |  | 19394
35 | Travelocity |  |  | 19383
36 | Apple I Phone |  |  | 19366
37 | Nuclear reactor controls |  |  | 19084
38 | IRS income tax analysis |  |  | 19013
39 | Cruise ship navigation |  |  | 18896
40 | MRI medical imaging |  |  | 18785
41 | Google search engine |  |  | 18640
42 | Amazon web site |  |  | 18080
43 | Order entry system |  |  | 18052
44 | Apple Leopard |  |  | 17884
45 | Linux |  |  | 17505
46 | Oil refinery process control |  |  | 17471
47 | Corporate cost accounting |  |  | 17378
48 | FEDEX shipping controls |  |  | 17378
49 | Tomahawk cruise missile |  |  | 17311
50 | Oil refinery process control |  |  | 17203
51 | ITT System 12 telecom |  |  | 17002
52 | Ask search engine |  |  | 16895
53 | Denver Airport luggage |  |  | 16661
54 | ADP Payroll application |  |  | 16390
55 | Inventory management |  |  | 16239
56 | EBAY transaction controls |  |  | 16233
57 | Patriot missile controls |  |  | 15392
58 | Second Life web site |  |  | 14956
59 | IBM IMS data base |  |  | 14912
60 | America On Line (AOL) |  |  | 14761
61 | Toyota robotic mfg. |  |  | 14019
62 | State wide child support |  |  | 13823
63 | Vonage VOIP |  |  | 13811
64 | Quicken 2006 |  |  | 11339
65 | ITMPI web site |  |  | 11033
66 | Motor vehicle registrations |  |  | 10927
67 | Insurance claims handling |  |  | 10491
68 | SAS statistical package |  |  | 10380
(Note: Applications between 1,000 and 10,000 function points comprise the majority of stand-alone programs,
components of larger systems, and scores of embedded and systems software applications for complex physical devices.
Many common applications such as Microsoft Word and Excel are in this size range.)
69 | Oracle CRM Features |  |  | 6386
70 | DNA Analysis |  |  | 6213
71 | Enterprise Java Beans |  |  | 5877
72 | Software renovation tool suite |  |  | 5170
73 | Patent data mining |  |  | 4751
74 | EZPass vehicle controls |  |  | 4571
75 | U.S. Patent applications |  |  | 4429
76 | Chinese submarine sonar |  |  | 4017
77 | Microsoft Excel 2007 |  |  | 3969
78 | Citizens bank on-line |  |  | 3917
79 | MapQuest |  |  | 3793
80 | Bank ATM controls |  |  | 3625
81 | NVIDIA graphics card |  |  | 3573
82 | Lasik surgery (wave guide) |  |  | 3505
83 | Sun D-Trace utility |  |  | 3309
84 | Microsoft Outlook |  |  | 3200
85 | Microsoft Word 2007 |  |  | 2987
86 | Artemis Views |  |  | 2507
87 | ChessMaster 2007 game |  |  | 2227
88 | Adobe Illustrator |  |  | 2151
89 | SpySweeper antispyware |  |  | 2108
90 | Norton anti-virus software |  |  | 2068
91 | Microsoft Project 2007 |  |  | 1963
92 | Microsoft Visual Basic |  |  | 1900
93 | Windows Mobile |  |  | 1858
94 | SPR KnowledgePlan |  |  | 1785
95 | All-in-one printer |  |  | 1780
96 | AutoCAD |  |  | 1768
97 | Software code restructuring |  |  | 1658
98 | Intel Math function library |  |  | 1627
99 | Sony PlayStation game controls |  |  | 1622
100 | PBX switching system |  |  | 1592
101 | SPR Checkpoint |  |  | 1579
102 | Microsoft Links golf game |  |  | 1564
103 | GPS navigation system |  |  | 1518
104 | Motorola cell phone |  |  | 1507
105 | Seismic analysis |  |  | 1492
106 | PRICE-S |  |  | 1486
107 | Sidewinder missile controls |  |  | 1450
108 | Apple I Pod |  |  | 1408
109 | Property tax assessments |  |  | 1379
110 | SLIM |  |  | 1355
111 | Microsoft DOS |  |  | 1344
112 | Mozilla Firefox |  |  | 1340
113 | CAI APO (original estimate) |  |  | 1332
114 | Palm OS |  |  | 1310
115 | Google Gmail |  |  | 1306
116 | Digital camera controls |  |  | 1285
117 | IRA account management |  |  | 1281
118 | Consumer credit report |  |  | 1267
119 | Laser printer driver |  |  | 1248
120 | Software complexity analyzer |  |  | 1202
121 | JAVA compiler |  |  | 1185
122 | COCOMO II |  |  | 1178
123 | Smart bomb targeting |  |  | 1154
124 | Wikipedia |  |  | 1142
125 | Music synthesizer |  |  | 1134
126 | Configuration control |  |  | 1093
127 | Toyota Prius engine |  |  | 1092
128 | Cochlear implant (internal) |  |  | 1041
129 | Nintendo Game Boy DS |  |  | 1002
(Note: Applications between 100 and 1,000 function points are primarily small embedded applications, plus
features and updates to larger systems. A number of single-purpose applications are in this range.)
130 | Casio atomic watch |  |  | 993
131 | Football bowl selection |  |  | 992
132 | COCOMO I |  |  | 883
133 | APAR analysis and routing |  |  | 866
134 | Computer BIOS |  |  | 857
135 | Automobile fuel injection |  |  | 842
136 | Anti-lock brake controls |  |  | 826
137 | Quick Sizer Commercial |  |  | 794
138 | CAI APO (revised estimate) |  |  | 761
139 | LogiTech cordless mouse |  |  | 736
140 | Function point workbench |  |  | 714
141 | SPR SPQR/20 |  |  | 699
142 | Instant messaging |  |  | 687
143 | Golf handicap analyzer |  |  | 662
144 | Denial of service virus |  |  | 138
145 | Quick Sizer prototype |  |  | 30.03
146 | ILOVEYOU computer worm |  |  | 22.17
147 | Keystroke logger virus |  |  | 14.73
(Note: There are few applications between 10 and 100 function points other than viruses and spyware.
However this size range is the most common for enhancements and new features for larger applications.)
148 | MYDOOM computer virus |  |  | 8.16
149 | APAR bug report |  |  | 3.85
Note: Applications between 1 and 10 function are usually bug repairs and small updates to larger applications.
Applications of this small size cannot be measured using standard IFPUG function points, but require
"micro-function points" for sizing.)
150 | Screen format change |  |  | 0.87
Table 50: Example of the Structure of a Fully Measured Software Project
(Note; Not every project performs all 25 activities, but this general example indicates the kind of data necessary for economic analysis.)
Average monthly salary = |  | 5000
Burden rate = |  | 50%
Fully burdened monthly rate = |  | 7500
Work hours per calendar month = |  | 132
Application size in FP = |  | 1500
Application type = |  | Systems
CMM level = |  | 1
Programming lang. = |  | C
LOC per FP = |  | 128
Activities | Staff | Monthly | Work Hours | Salary | Burdened
| Function Point | Function Point | per | Cost per | Cost per | Schedule |  | Effort | Effort
| Assignment | Production | Function Point | Function Point | Function Point | Months | Staff | Months | Hours
| Scope | Rate
01 Requirements | 500 | 200 | 0.66 | 25 | 37.5 | 2.5 | 3 | 7.5 | 990
02 Prototyping | 500 | 150 | 0.88 | 33.33 | 50 | 3.33 | 3 | 10 | 1320
03 Architecture | 1000 | 300 | 0.44 | 16.67 | 25 | 3.33 | 1.5 | 5 | 660
04 Project Plans | 1000 | 500 | 0.26 | 10 | 15 | 2 | 1.5 | 3 | 396
05 Initial Design | 250 | 175 | 0.75 | 28.57 | 42.86 | 2.86 | 3 | 8.57 | 1131
06 Detail Design | 250 | 150 | 0.88 | 33.33 | 50 | 1.67 | 6 | 10 | 1320
07 Design Reviews | 200 | 225 | 0.59 | 22.22 | 33.33 | 0.89 | 7.5 | 6.67 | 880
08 Coding | 150 | 25 | 5.28 | 200 | 300 | 6 | 10 | 60 | 7920
09 Reuse acquisition | 500 | 1000 | 0.13 | 5 | 7.5 | 0.5 | 3 | 1.5 | 198
10 Package purchase | 2000 | 2000 | 0.07 | 2.5 | 3.75 | 1 | 0.75 | 0.75 | 99
11 Code inspections | 150 | 75 | 1.76 | 66.67 | 100 | 2 | 10 | 20 | 2640
12 Ind. Verif. & Valid. | 1000 | 250 | 0.53 | 20 | 30 | 4 | 1.5 | 6 | 792
13 Configuration mgt. | 1500 | 1750 | 0.08 | 2.86 | 4.29 | 0.86 | 1 | 0.86 | 113
14 Integration | 750 | 350 | 0.38 | 14.29 | 21.43 | 2.14 | 2 | 4.29 | 566
15 User documentation | 1000 | 75 | 1.76 | 66.67 | 100 | 13.33 | 1.5 | 20 | 2640
16 Unit testing | 200 | 150 | 0.88 | 33.33 | 50 | 1.33 | 7.5 | 10 | 1320
17 Function testing | 250 | 150 | 0.88 | 33.33 | 50 | 1.67 | 6 | 10 | 1320
18 Integration testing | 250 | 175 | 0.75 | 28.57 | 42.86 | 1.43 | 6 | 8.57 | 1131
19 System testing | 250 | 200 | 0.66 | 25 | 37.5 | 1.25 | 6 | 7.5 | 990
20 Field (Beta) testing | 1000 | 250 | 0.53 | 20 | 30 | 4 | 1.5 | 6 | 792
21 Acceptance testing | 1000 | 350 | 0.38 | 14.29 | 21.43 | 2.86 | 1.5 | 4.29 | 566
22 Independent testing | 750 | 200 | 0.66 | 25 | 37.5 | 3.75 | 2 | 7.5 | 990
23 Quality assurance | 1500 | 250 | 0.53 | 20 | 30 | 6 | 1 | 6 | 792
24 Installation/training | 1500 | 250 | 0.53 | 20 | 30 | 6 | 1 | 6 | 792
25 Project management | 1000 | 75 | 1.76 | 66.67 | 100 | 13.33 | 1.5 | 20 | 2640
Cumulative Results | 420 | 6 | 22 | 833.29 | 1249.94 | 24.65 | 3.57 | 249.99 | 32998
For additional information and data by Capers Jones see:
Estimating Software Costs, McGraw Hill, 2007
Applied Software Measurement, McGraw Hill, 2008
Software Assessments, Benchmarks, and Best Practices, Addison Wesley, 2000
Copyright © 2008 by Capers Jones & Associates LLC. All rights reserved.
Capers Jones | Email: CJonesiii@cs.com